## Slide 1: Weekly Status Report
Completed Discovery session.
Received UAT server credentials and Perdix API (Login API) for Integration from client.
Downloaded the source code, data files and mySql database.
UI wireframe (high-level sketch) is ready for review.
Scope Document preparation – In progress. ETA Nov 9.
Setting up the Moodle in local environment for development – In Progress. ETA Nov 10.
Status |  | Project Manager | VEDHA MUKUNDHAN | Sponsor | HUMA TARIQ | Date | Nov 07, 2022
Last Week Activities
Will complete the Moodle Setup in local & cloud.
Continue the development of Group 2 & 3 tasks.
UI Wireframe / Scope Document will be shared for review and sign off.
Will check the Perdix API integration.
Plan for This Week
Need Attention
Under Control
On Track
Legends
Schedule
Issues / Action Items
S. No. | Description | Comments | Severity | Status | Owner | ETA
1 | API Credentials | Need valid Login credentials to integrate and continue. | Medium | Open | Dvara | 08/11/22
2 | Dev environment set up | Setting up the development environment both local and cloud. | Medium | Open | Integra | 10/11/22
3 | Mitigation | Development activities of Group 2, 3 & 4 are on track. | High | NA | Integra | NA
4 | UI / Scope Document | Review and sign off on both UI wireframe and scope document. | Medium | Open | Integra | TBD
07/11
Activities | Wk1 (31/10) | Wk2 (07/11) | Wk3 (14/11) | Wk4 (21/11) | Wk5 (28/11) | Wk6 (05/12) | Wk7 (12/12) | Wk8 (19/12)
Requirements & Discovery |  |  |  |  |  |  |  | 
Development & Testing |  |  |  |  |  |  |  | 
UAT Deployment |  |  |  |  |  |  |  | 
UAT |  |  |  |  |  |  |  | 
UAT Sign Off |  |  |  |  |  |  |  | 21-Dec
Go-Live |  |  |  |  |  |  |  | 23-Dec